## Sheet1
Iteration Plan
S.No. | Features | FYP-I Iterations
|  | Monthly Iteration-I | Monthly Iteration-II | Monthly Iteration-III | Monthly Iteration-IV
F1 | Calculate number of teeth's | Requirements(50%) | Requirements(100%)
|  |  | Implementation(50%) | Implementation(100%)
Testing(100%)
F2 | Calculate Size of the Gear | Requirements (25%) | Requirements (50%) | Requirements (100%)
|  |  | Implementation(25%) | Implementation(75%) | Implementation(100%)
Testing(100%)
F3 | Calculate Surface Roughness | Requirements (25%) | Requirements (50%) | Requirements (100%)
|  |  | Implementation(25%) | Implementation(50%) | Implementation(75%)
Output Features |  | F1, F2, F3 | F1, F2, F3 | F1, F2, F3 | F2, F3
S.No. | Features | FYP-2 Iterations
F1 | Design and develop GUI
|  |  | Implementation(25%) | Implementation(75%) | Implementation(100%)
Testing(100%)
F2 | Calculate Surface Roughness
|  | Implementation(75%) | Implementation(75%) | Implementation(90%) | Implementation(100%)
Testing(100%)
Output Features |  | F2 | F1, F2 | F1, F2 | F1, F2